## Team
Initials | First | Last | Email | GitHub Username
DA | Deeptidevi | Agrawal | dagrawa2@stevens.edu | Deepti-SSW555
AA | Anurag | Aman | aaman1@stevens.edu | anurag-aman
DN | Dishant | Naik | dnaik3@stevens.edu | DishantNaik
DP | Dhruv | Patel | dpate111@stevens.edu | dhrupatel97
NN | Neil | Naidu | nnaidu@stevens.edu | neilvarunnaidu
PK | Pradeep | Kumar | psentham@stevens.edu | Pradeep6149
|  |  | GitHub Repository: | https://github.com/DishantNaik/CS_555_Project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US29 | List deceased | DA | Completed
1 | US30 | List living married | DA | Completed
4 | US28 | Order siblings by age | DA | Planned
1 | US31 | List living single | DA | Completed
3 | US33 | List orphans | DA | Completed
2 | US35 | List recent births | DA | Completed
2 | US36 | List recent deaths | DA | Completed
3 | US38 | List upcoming birthdays | DA | Completed
2 | US01 | Dates before current date | AA | Completed
2 | US02 | Birth before marriage | AA | Completed
3 | US03 | Birth before death | AA | Completed
3 | US06 | Divorce before death | AA | Completed
4 | US07 | Less then 150 years old | AA | Completed
1 | US17 | No marriages to descendants | AA | Completed
1 | US21 | Correct gender for role | AA | Completed
4 | US25 | Unique first names in families | AA | Completed
1 | US04 | Marriage before divorce | DP | Completed
1 | US05 | Marriage before death | DP | Completed
3 | US15 | Fewer than 15 siblings | DP | Completed
2 | US16 | Male last names | DP | Completed
4 | US23 | Unique name and birth date | DP | Completed
2 | US27 | Include individual ages | DP | Completed
3 | US34 | List large age differences | DP | Completed
4 | US40 | List individual without children | DP | Completed
4 | US08 | Birth before marriage of parents | DN | Completed
3 | US09 | Birth before death of parents | DN | Completed
1 | US10 | Marriage after 14 | DN | Completed
3 | US14 | Multiple births <= 5 | DN | Completed
2 | US22 | Unique IDs | DN | Completed
2 | US32 | List multiple births | DN | Completed
1 | US39 | List upcoming anniversaries | DN | Completed
4 | US42 | Reject illegitimate dates | DN | Completed
3 | US11 | No bigamy | NN | Not Planned
3 | US12 | Parents not too old | NN | Not Planned
1 | US13 | List infant mortalities | NN | Completed
2 | US18 | Siblings should not marry | NN | Planned
2 | US19 | All | NN | Planned
1 | US43 | No death fraud | NN | Completed
1 | US44 | List deceased adults without spouses | NN | Completed
| US45 | List all maiden names | NN | Not Planned
2 | US20 | Aunts and uncles | PK | Completed
3 | US24 | Unique families by spouses | PK | Completed
3 | US26 | Corresponding entries | PK | Completed
4 | US37 | List recent survivors | PK | Planned
4 | US41 | Include partial dates | PK | Planned
1 | US46 | List living married Male | PK | Completed
2 | US47 | List people with single parent | PK | Completed
1 | US48 | List living married Female | PK | Completed

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2020-09-21 | 48 |  | 0
2020-10-05 | 34 | 14 | 552 | 1102 | 30.0544
2020-10-12 | 34 | 14 | 552 | 1102 | 30.1 | Refactoring Week
2020-10-26 | 22 | 12 | 976 | 365 | 69.698
2020-11-10
2020-12-05
2020-12-25

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed date
US29 | List deceased | DA | Completed | 50 | 120 | 33 | 90 | 2020-09-27
US30 | List living married | DA | Completed | 50 | 120 | 11 | 60 | 2020-10-04
US31 | List living Single (Paired Programming) | DA/AA | Completed | 50 | 120 | 12 | 30 | 2020-10-04
US17 | No marriage to descendants | AA | Completed | 100 | 120 | 15 | 60 | 2020-10-04
US21 | Correct gender for role (Paired Programing) | AA/DA | Completed | 100 | 120 | 15 | 60 | 2020-10-04
US10 | Marriage after 14 | DN | Completed | 100 | 120 | 28 | 30 | 2020-10-02
US39 | List upcoming anniversaries | DN | Completed | 100 | 120 | 43 | 90 | 2020-09-27
US04 | Marriage before divorce | DP | Completed | 90 | 120 | 21 | 90 | 2020-10-02
US05 | Marriage before death | DP | Completed | 90 | 120 | 27 | 90 | 2020-09-27
US43 | No death Fraud | NN | Completed | 90 | 100 | 23 | 80 | 2020-10-05
US44 | List deceased with no spouses | NN | Completed | 90 | 120 | 23 | 100 | 2020-10-05
US13 | List Infant Mortalities | NN | Completed | 100 | 120 | 23 | 90 | 2020-10-02
US46 | List of living married male | PK | Completed | 100 | 120 | 38 | 116 | 2020-10-02
US48 | List of living married female | PK | Completed | 90 | 120 | 38 | 116 | 2020-10-02
Review Results
Keep doing:
Checking for updates from github
Updating each other about any problem
Avoid:
Less communication

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US35 | List recent births | DA | Completed | 25 | 60 | 15 | 30 | 2020-10-26
US36 | List recent deaths | DA | Completed | 25 | 60 | 15 | 30 | 2020-10-26
US32 | List multiple births | DN | Completed | 60 | 90 | 25 | 25 | 2020-10-26
US22 | Unique IDs | DN | Completed | 40 | 90 | 20 | 15 | 2020-10-25
US27 | Include Individual ages | DP | Completed | 60 | 100 | 15 | 20 | 2025-10-01
US16 | Male last name | DP | Completed | 60 | 100 | 48 | 40 | 2025-10-01
US01 | Date before current date | AA | Completed | 60 | 100 | 23 | 30 | 2020-10-26
US02 | Birth Before marriage | AA | Completed | 60 | 100 | 17 | 30 | 2020-10-26
US20 | Aunts and Uncle | PK | Completed | 60 | 100 | 62 | 45 | 2020-10-29
US47 | List of people with single parent | PK | Completed | 40 | 100 | 16 | 30 | 2020-10-26
US18 | Sibling should not marry | NN | Completed | 60 | 90 | 29 | 30 | 2020-10-30
US19 | Female last name | NN | Completed | 50 | 90 | 40 | 45 | 2020-10-31
Make 2 lists:
Things want to keep doing |  |  |  | Things that want to avoid doing in the future
1. Reuse code |  |  |  | 1. Wait untill last moment
2. Refactor code after each sprint |  |  |  | 2. Avoid duplicate code
3. Follow function naming standards |  |  |  | 3. Avoid complex code
4. Write valid testcases |  |  |  | 4. Avoid breaking testcases
5. Run testcases after integrating code in each sprint
6. Update testdata for each usecase

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US15 | Fewer than 15 sibiling | DP | Completed | 30 | 60 | 28 | 40 | 2020-11-09
US34 | List large age difference | DP | Completed | 30 | 60 | 34 | 50 | 2020-11-09
US09 | Birth before death of parents | DN | Completed | 120 | 120 | 86 | 110 | 2020-11-09
US14 | Multiple births <= 5 | DN | Completed | 60 | 60 | 42 | 45 | 2020-11-09
US33 | List orphans | DA | Completed | 25 | 60 | 41 | 100 | 2020-11-09
US38 | List upcoming birthdays | DA | Completed | 25 | 60 | 24 | 60 | 2020-11-09
US03 | Birth before death | AA | Completed | 30 | 60 | 35 | 60 | 2020-11-09
US06 | Divorce before death | AA | Completed | 30 | 60 | 32 | 70 | 2020-11-09
US24 | Unique families by spouses | PK | Planned | 50 | 60 | 25 | 60 | 2020-11-09
US26 | Corresponding entries | PK | Planned | 60 | 60 | 61 | 60 | 2020-11-09
US11 | No Bigamy | NN | Planned | 60 | 60
US12 | Parents not too old | NN | Planned | 60 | 60
Make 2 lists:
Things want to keep doing |  |  |  | Things that want to avoid doing in the future
1. Reuse code |  |  |  | 1. Wait untill last moment
2. Refactor code after each sprint |  |  |  | 2. Avoid duplicate code
3. Follow function naming standards |  |  |  | 3. Avoid complex code
4. Write valid testcases |  |  |  | 4. Avoid breaking testcases
5. Run testcases after integrating code in each sprint |  |  |  | 5. Keep standup calls short and specific to the point
6. Update testdata for each usecase
7. Identify bugs/defects
8. Prioritize and fix bugd/defetcs
9. Lend helping hands to other developers, if required

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US28 | Order siblings by age | DA | Planned | 40 | 90
US25 | Unique first names in families | AA | Completed | 30 | 75 | 30 | 30 | 2020-11-30
US07 | Less then 150 years old | AA | Completed | 30 | 75 | 25 | 35 | 2020-11-30
US08 | Birth before marriage of parents | DN | Planned | 50 | 60 | 23 | 30 | 2020-11-30
US42 | Reject illegitimate dates | DN | Planned | 50 | 60 | 89 | 35 | 2020-11-30
US23 | Unique name and birth date | DP | Planned | 60 | 70 | 32 | 30 | 2020-11-24
US40 | List individual without children | DP | Planned | 40 | 30 | 18 | 15 | 2020-11-29
US37 | List recent survivors | PK | Planned | 60 | 70
US41 | Include partial dates | PK | Planned | 70 | 80

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | List individual without children | List all Individual who do not have children
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)
US43 | No death fraud | Death should be after birthdate and not vice versa
US44 | Accurate birthdates | Birthdate should take into account parent's birth and be at least post their puberty
US45 | List all maiden names | List the maiden names of all females who have been married
US46 | List living married Male | List all living married people who are male in a GEDCOM file
US47 | List people with single parent | List all people in a GEDCOM file who have either their father or their mother
US48 | List living married Female | List all living married people who are female in a GEDCOM file